## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone1: Source a tablet vendor
Search for a suitable vendor for the tablet |  |  |  | 4
Generate quotes and review costs |  |  |  | 3
Vendor timeline and deliverables schedule | Delivery may be affected by the amount of stock Terrific Tablets have when the order is placed. The company is also set to release an upgraded version of the tablet. |  |  | 9
Create contracts and statements of work for vendors |  |  |  | 3
Milestone2: Install and test tablets
Source an electrician for wiring installations | Extent of wiring required on both the locations to be known. Check with the electrcians about the best time to work and notify GM whether their location needs to be closed for wiring. |  |  | 4
Software update and installation |  |  |  | 3
Test Tablet systems after installation |  |  |  | 4
Select appropriate package from Terrific Tablets involving the marketing team | Choose Customer Branding and Design packages |  |  | 2
Revamp the menu based on requirements | Carter may do some research about what’s trending and test things out for a few weeks. |  |  | 10
Upload the new menu and coupons to the tablet |  |  |  | 1
Test user interface and design |  |  |  | 1
Test the interface to talk directly to the chef |  |  |  | 0
Milestone3: Source vendor for cash register and install and test the system
Source for a vendor to combine cash register with the tablet |  |  |  | 3
Install the cash register and test the system integration |  |  |  | 2
Milestone4: Training staffs and key members
Plan and schedule meetings for training |  |  |  | 1
Schedule staff meetings with GM to discuss anything that could affect waitsatff tips | Discuss the idea of including the tips in the price of the food, and restructure pay and incentives for the staff since, this idea failed in waterfront location and had huge impact on staff morale. |  |  | 1
Train key staff members first and then train the whole team | Waitstaff tends to resist changing the way they intearct with customers. If someone in house does the training they're more likely to get on board. |  |  | 14
Training for staffs on how to update menu in real time | If an item is no longer available it can be updated in real time from the admin back-end of the software, which can be accessed on the office computer and the staff should be trained on this. |  |  | 0
Milestone5: Realtime testing the whole project before launch
Invite friends and family to do a test run on tablets | Invite friends and family on a Sunday morning to test the tablets |  |  | 1
Milestone6: Swap the tablets
Receive and swap the old tablets with the new ones post launch | The swap must be agreed with no extra costs and the discount should be available for the older models |  |  | 14

## Task Brainstorm
Task Brainstorm
# | Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
1 | Milestone1: Source a tablet vendor |  | 4
1.1 | Search for a suitable vendor for the tablet
1.2 | Generate quotes and review costs |  | 3
1.3 | Vendor timeline and deliverables schedule | Delivery may be affected by the amount of stock Terrific Tablets have when the order is placed. The company is also set to release an upgraded version of the tablet. | 9 | 7 | 9 | 11 | M
1.4 | Create contracts and statements of work for vendors |  | 3
2 | Milestone2: Install and test tablets
2.1 | Source an electrician for wiring installations | Extent of wiring required on both the locations to be known. Check with the electrcians about the best time to work and notify GM whether their location needs to be closed for wiring. | 4 | 4.5 | 4 | 5 | L
2.2 | Software update and installation |  | 3 | 1 | 2 | 4 | L
2.3 | Test Tablet systems after installation |  | 4
2.4 | Select appropriate package from Terrific Tablets involving the marketing team | Choose Customer Branding and Design packages | 2 |  |  |  | H
2.5 | Revamp the menu based on requirements | Carter may do some research about what’s trending and test things out for a few weeks. | 10 | 7 |  | 14 | H
2.6 | Upload the new menu and coupons to the tablet |  | 1 | 0.5 | 1 | 2
2.7 | Test user interface and design |  | 1
2.8 | Test the interface to talk directly to the chef |  | 0
3 | Milestone3: Source vendor for cash register and install and test the system
3.1 | Source for a vendor to combine cash register with the tablet |  | 3
3.2 | Install the cash register and test the system integration |  | 2
4 | Milestone4: Training staffs and key members
4.1 | Plan and schedule meetings for training |  | 1 |  |  | 7
4.2 | Schedule staff meetings with GM to discuss anything that could affect waitsatff tips | Discuss the idea of including the tips in the price of the food, and restructure pay and incentives for the staff since, this idea failed in waterfront location and had huge impact on staff morale. | 1
4.3 | Train key staff members first and then train the whole team | Waitstaff tends to resist changing the way they intearct with customers. If someone in house does the training they're more likely to get on board. | 14 | 10 | 14 | 21 | M
4.4 | Training for staffs on how to update menu in real time | If an item is no longer available it can be updated in real time from the admin back-end of the software, which can be accessed on the office computer and the staff should be trained on this. | 0 | 0.2 | 0.4 | 0.5 | L
5 | Milestone5: Realtime testing the whole project before launch
5.1 | Invite friends and family to do a test run on tablets | Invite friends and family on a Sunday morning to test the tablets | 1 | 1 | 1.5 | 2 | H
6 | Milestone6: Swap the tablets
6.1 | Receive and swap the old tablets with the new ones post launch | The swap must be agreed with no extra costs and the discount should be available for the older models | 14 | 9 | 14 | 21 | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Tabletop tech | Tabletop tech speeds up service and boosts profits | 2022-03-01
Best Uses for Tablets at Your Restaurant | Best Uses for Tablets at Your Restaurant | 2022-03-01

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Achieve average ticket time of 8 minutes for appetizers and 12-515 minutes for entrees | Are the delays in service decreasing? | The Table turn around time decreases by 30 mins | FALSE
Customer Satisfaction | Achieve average table turn around time by 30 minutes | Are the revenues increasing? | Increase in average daily guest counts by 10% | FALSE
Customer Satisfaction | Maintain a checkout time of 1 minute or less by ensuring seamless and easy to navigate check out process. | Are customers satisified with the delivery check out system? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | FALSE
Customer Satisfaction | Maintain the customers report on technical issues each week to less than 5% | Are the tablets functioning properly? | 98% of customers who use tablets receive the correct order | FALSE
Customer Satisfaction | Achieve an order accuracy of 98% |  |  | FALSE
Customer Satisfaction | Achieve average wait time for the customers to less than 10 minutes |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Achieve average ticket time of 8 minutes for appetizers and 12-15 minutes for entrees | Are the delays in service decreasing? | The Table turn around time decreases by 30 mins | Did the order arrive at the right time? | Yes/No | Yes | No
Achieve average table turn around time by 30 minutes | Are the revenues increasing? | Increase in average daily guest counts by 10% | What was the overall experience using the tablet for ordering? | Open-ended | Open Ended
Maintain a checkout time of 1 minute or less by ensuring seamless and easy to navigate check out process. | Are customers satisified with the delivery check out system? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate our delivery check out system? | Scaled | Very Satisfied | Somewhat satisfied | Neither satisfied nor dissatisfied | Somewhat dissatisfied | Very dissatisfied
Maintain the customers report on technical issues each week to less than 5% | Are the tablets functioning properly? | 98% of customers who use tablets receive the correct order | What are the technical issues you are facing while placing an order? | Multiple choice | User interface is not user friendly | Touch sensitive issues | Prices are not displayed for some food items | System is not allowing to place order when all the items are selected | Check out page not loading
Achieve an order accuracy of 98% | Are the customers being served for what they asked for? | 98% of customers who use tablets receive the correct order | Most of the orders were delivered accurately | True/False | TRUE | FALSE
|  |  | Overall experience using the tablets to order food | Open-ended | Open Ended
|  |  | Compared to conventional ordering, how efficient was tablet enabled food ordering and checkout system? | Open-ended | Open Ended
|  |  | Would you recommend our restaurant experience to your friends and family | Yes/No | Yes | No
|  |  | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate our tablet's user interface? | Scaled | Very Satisfied | Somewhat satisfied | Neither satisfied nor dissatisfied | Somewhat dissatisfied | Very dissatisfied
|  |  | Provide feedback on how to improve the overall dining experience | Open-ended | Open Ended