## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Overall tablet experience | 72% of the customer felt the experience was above average. | Encourage customers to use tablets every time they order and increase the order accuracy.
Customers | Needs improvement | Tablet navigation experience | 52% of the customer felt problems to navigate through the tablet. | Make the tablet more user friendly, include clear instructions on how to navigate.
Customers | Went well | Wait time for food | 56% of customer recived their food within 20 minutes of ordering. | Check where the delay occurs and bridge the gap through training the staffs to quickly process the food and check for quality before it is presented.
Customers | Went well | Order accuracy | 72% of the order were accurately prepared asper the customer needs. | Train back end staffs to acheieve the target of 98% order accuracy.
Customers | Needs improvement | Tablet ordering experience | Only 40% of customer felt tablet experience better than traditional one. | Make the user experience better which would compel the customer to use the tablet more instead of a waiter.
Customers | Needs improvement | Technical issues with the tablet | 12% of the customers faced issues like frozen screen, glitch while ordering etc. | Software team to run a test on the tablets and try to minimize the technical issues and also train the staff to help customers when they face such issues in future.
Project team | Needs improvement | Table turn time | Although the food came out on time, the table turn time stayed about the same. | Implementation of new updates to kitchen operations may help decrease the table turn time.
Project team | Went well | Communication with vendor | Weekly calls with vendors helped us stay on track and clarify task dependencies. | Request the vendor to keep this cadence for the next series of rollouts.
Project team | Went well | Implementation of new updates to kitchen | The new updates for the kitchen operation helped to cope with the ticket flow. | Set up a meeting with the kitchen managers to discuss on the issues faced during the roll out.
Project team | Needs improvement | POS integration | Technical issues were discovered during the integration and were fixed | Update the process manual so that the solution is easy to find next time that issue comes up.
Project team | Went well | Customer survey | The results indicate that we met most of our customer satisfaction standards | Use the data for future research that may help us to improve the areas where more attention is needed to increase customer satisfaction.
Project team | Needs improvement | Operations & Resource planning | Few internal operational issues were discovered, Some of the vacation time were not accounted during the planning phase | Understand each location’s history before planning gets underway and make sure we plan things properly based on everyone’s availability.